## Sheet1
International Particle Accelerator Conference
Richmond, VA
April 29-May 8, 2015
Association Contact:
Anita Chapman, CMP
804-339-2006 / anita@helmsbriscoe.com |  | Revised 4-26-2015 AC
Tuesday, April 28, 2015
Date/Time | Event | Location/Room Name | Room Set-up | # of people | A/V |  | NOTES | POC
8am Midnight | Storage ONLY for Audio Visual and IT No meetings | RCC-BUSINESS CENTER on 24 hour hold | clean and clear for storage | 10 | no A/V |  | No food and no set until tomorrow; Bryan please give Anthony one of the keys to the Business Office upon arrival on Tuesday to place stored item; Anita to have 9 total keys to the Business Center-Bryan will give them to her numbered on Wednesday. Will need three keys to the attached office. | TRS will arrive on May 1
Wednesday, April 29, 2015
Date/Time | Event | Location/Room Name | Room Set-up | # of people | A/V | Photographer | NOTES | POC
24 hour hold--SET UP | Editorial Room | E-11B | Set up from Anthony | 26 | no A/V | No | must be locked and keyed. # of keys TBD; Need to order 26 comfortable chairs (Evelyn to arrange the for this room; room on 24 hour hold and will remain in the same set but will need to be cleaned and cleared. Will need small trash cans (one for every two persons) and two large containers | Staff and volunteers to be provided by Jefferson Lab
24 hour hold--SET UP | Food and Beverage for Editors and Authors | RCC-E-11C |  | 20 |  | No
24 hour hold--SET UP | Authors Reception Room | RCC-E-11-A |  |  |  | No
24 hour hold--SET UP | Storage for Audio Visual and Anthony | Business Center |  |  |  | No
Thursday, April 30, 2015
Date/Time | Event | Location/Room Name | Room Set-up | # of people | A/V |  | NOTES | POC
24 hour hold | Editorial Room | RCC-E11B | total of 9 work stations on 24 hour hold until Friday, May 8two computer work stations per 6 ft table facing doors. Must be locked | 29 |  | No | Existing | Staff and volunteers to be provided by Jefferson Lab
24 hour hold--SET UP | Storage Room ONLY for Audio Visual | RCC-BUSINESS CENTER on 24 hour hold |  |  |  | No | Existing
24 hour hold--SET UP | Food and Beverage for Editors and Authors | RCC-E-11C |  | 20 |  | No
24 hour hold--SET UP | Authors Reception Room | RCC-E-11-A |  | 7 |  | No | existing
Friday, May 1, 2015
Date/Time | Event | Location/Room Name | Room Set-up | # of people | A/V |  | NOTES | POC
24 hour hold | Editorial Room | RCC-E11B | total of 9 work stations on 24 hour hold until Friday, May 8two computer work stations per 6 ft table facing doors. Must be locked | 29 | printers, power strips and laptops needed | No | Existing | Anthony and Evelyn Food and Beverage for 25 ppl
8am-5pm | Registration set up | Registration Lobby |  |  | printers, power strips and laptops needed | No |  | Anita
24 hour hold | Press Room | RCC-E22-A | (6) six foot tables set as workstations with internet connections and power supply hookups; room will have camera area in corner as well. | 6 | printers, power stips and laptops needed | No |  | John will be in charge of this room for PR
24 hour hold | Authors Reception Room | RCC-E-11-A |  |  |  | No |  | Anthony and Evelyn
24 hour hold | Staff Office | Registration Office #2 |  |  | printers, power stips and laptops needed | No
24 hour hold | OPEN MEETING ROOM (SET ON THIS DAY) | RCC-E10A |  |  | LCD Projector and Package | No | must be locked and keyed. # of keys TBD | No staffing needed
24 hour hold--SET UP | Storage Room ONLY for Audio Visual; Office for Fulvia, Andrew, Erin and Stan | RCC-BUSINESS CENTER on 24 hour hold |  |  |  | No | LOC MEETING LOCATION | Anita
Saturday, May 2, 2015-AIRPORT SHUTTLE RUNS FROM 8AM-8:30PM
Date/Time | Event | Location/Room Name | Room Set-up | # of people | A/V |  | NOTES | POC
24 hour hold | Editorial Room | RCC-E11B | total of 9 work stations on 24 hour hold until Friday, May 8two computer work stations per 6 ft table facing doors. Must be locked | 29 | printers, power stips and laptops needed | No | Existing | Anthony and Evelyn
24 hour hold | Authors/Editors F&B and Storage | RCC-E11-C | rounds with tables for food | 35 |  | No |  | No staffing needed
24 hour hold | Registration Set Up | RCC-Registration Lobby | Build registration station with 8 registration areas |  | printers, power strips and laptops needed | No |  | Anita
24 hour hold | Authors Reception Room | RCC-E11A | four six foot tables flush to the wall with printer and binders on the back walls. Three six foot tables facing the door with two computer work stations | 7 |  | Yes | yes, tbd | Anthony and Evelyn
24 hour hold | Press Room | RCC-E22-A | (6) six foot tables set as workstations with internet connections and power supply hookups; room will have camera area in corner as well. | 6 |  | No |  | John will be in charge of this room for PR
24 hour hold | Paper Café | RCC-E10C |  |  |  | No | yes, tbd | Anthony
24 hour hold | Speaker Ready Room | RCC-E10D | Six foot tables around the perimeter of the room to accommodate 20 computers and work stations; 1 printer in the room | 20 |  | No | yes, tbd | Anthony
24 hour hold | Business Office | RCC-Registration 1 |  | 2 |  | No | existing set with another 6 ft table for working station | Pam and Stephanie
24 hour hold | Staff Office #2 | RCC-Registration 2 |  | 20 |  | No | six foot tables around the perimeter of the room and one large round in the center of the room | Anita
4-6pm | Pre-Con with the Richmond Regional Tourism, Richmond Convention Center, and the Richmond Marriott | RCC-Board Room |  | TBA |  | No | Attending from LOC-Andrew Hutton, Fulvia Pilat, Erin Clifton, Stephanie Vernimere, Evelyn Akers, Anthony Cuffe and Todd Satagota | Bryan
24 hour hold | OPEN MEETING ROOM | RCC-E10A |  |  | Existing from previous meeting | No | yes, tbd
After Midnight | Exhibit Hall set up and Exhibits Inc to set 33 poster session boards to accommodate 130 Student Poster Sessions | RCC-Exhibit Hall A | (100) 10x10 booths | 1200 | no A/V | No | See Diagram | Anita
Sunday, May 3, 2015-AIRPORT SHUTTLE RUNS FROM 8AM-8:30PM; HOTEL SHUTTLE RUNS FROM 7:45AM-9:45PM
Date/Time | Event | Location/Room Name | Room Set-up | # of people | A/V |  | NOTES | POC
24 hour hold | Editorial Room | RCC-E11-B | two computer work stations per 6 ft table facing doors. Must be locked | 29 | printers, power stips and laptops needed | Yes | Existing | Anthony; per Evelyn the JACOW Training Meeting will take place in the Editors Room from 12:30-2pm
24 hour hold | Authors/Editors F&B and Storage | RCC-E11-C | rounds with tables for food and buffet station | 35 | no A/V | Yes | Existing | Anthony
24 hour hold-Registration Times from 8AM-8PM | Registration | RCC-Registration Lobby | Existing | FLOW | printers, power stips and laptops needed | Yes | Existing | Anita to hire 8 people to work the desk; lead-Jeannie Powers; NOTE NURSING MOTHERS ROOM IN THE SMALL ROOM NEAR B15C
24 hour hold | Authors Reception Room | RCC-E11A | four six foot tables flush to the wall with printer and binders on the back walls. Three six foot tables facing the door with two computer work stations | 7 | printers, power stips and laptops needed | Yes | Existing | Anthony
24 hour hold | Paper Café | RCC-E10C | existing |  | printers, power stips and laptops needed | Yes | Existing | Anthony
24 hour hold | Press Room | RCC-E22-A | (6) six foot tables set as workstations with internet connections and power supply hookups; room will have camera area in corner as well. | 6 | printers, power stips and laptops needed | Yes |  | John will be in charge of this room for PR
24 hour hold | Speaker Ready Room | RCC-E10D |  |  | printers, power stips and laptops needed | Yes | Existing | Anthony
6AM-7AM | STUDENT POSTER SESSION SET UP BY EXHIBITS INC | Registration Lobby |  |  | no A/V | No | Existing | Todd
9AM-5:30PM | Accelerator Stewardship Test Facility Pilot | Marriott-Salons 1-4 |  | 40 | LCD and support package --note, contracted to use the Marriott's A/V team for all meeting space at the Marriott | No |  | Donna Nevels and Dr. Eric Colby OakRidge is contact
9AM-5:30PM | Accelerator Stewardship Test Facility Pilot | Marriott-Salon 5 |  | 20 | LCD and support package --note, contracted to use the Marriott's A/V team for all meeting space at the Marriott | No |  | Donna Nevels and Dr. Eric Colby OakRidge is contact
10AM -10:30AM | LOC Brief Staff Meeting | Business Center |  | 15 |  | Yes |  | Fulvia to lead
NOON-7PM; 2-6PM POSTER SESSIONS ARE OPEN | STUDENT POSTER SESSION PRESENTERS SET UP from NOON -1:30pm; Student poster sessions will run from 2-6pm | Registration Lobby |  |  | no A/V | Yes | Existing; ADD A WATER STATION TO THIS EVENT FROM 4-6PM | Todd
24 hour hold | Business Office | RCC-Registration 1 |  | 2 | printers, power stips and laptops needed | No | existing desk with additional 6 foot working station | Anita
24 hour hold | Staff Office Breakroom | RCC-Registration 2 | 25 |  | no A/V | No | Existing
24 hour hold | Storage | RCC-E10A |  |  | no A/V | No
NOON-6PM | Student Poster Sessions Judges | RCC-E10B | U-Shape; 2 per 6 ft | 30 | LCD and support package; TRS will need | YES | Headtable for three people; set in U-Shape | Evelyn is in charge of this room
8AM-4pm | Set up by Exhibits Inc--still pending approval on an earlier time which will be confirmed 30 days out | RCC-Exhibit Hall A | Needs to be set by Exhibits Inc. overnight and ready for vendors by noon |  | no A/V | Yes |  | Vendors must be set and at their booths by 6pm
NOON-6PM | Vendor move in--all vendors must be set and ready by 6pm. Doors will open at 6pm | RCC-Exhibit Hall A | Exhibits must be set up and ready by 5:45pm |  |  | Yes | Need to arrrange water stations on the show floor for set up | Anita to provide staffing for exhibit hall management with Exhibits Inc; FOUR SECURITY OFFICERS WILL NEED TO BE HIRED FROM NOON - 10PM AND TWO FROM 10PM-7AM
5:30pm-Midnight | APS-DPB Executive Committee (EC) Meeting with open bar and dinner from 5:30-7:30PM | Marriott A-D | U-Shape; 2 per 6 ft with chairs flush to the wall around the perimeter of the room; | 20 | Note---Moved from Marriott to Convention Center | Yes | U-Shape only per Stan Shriber | We plan and pay this. confirmed via Fulvia with Stan Shriber; we will need to determine the menu for dinner and budget? THIS WILL BE ON OUR MASTER ACCOUNT AND WILL BE CHARGED BACK TO THE LOAN FROM APS
6pm-9pm | Welcome Reception-Wine Tasting-Taste of Virginia | RCC-Exhibit Hall A | See Diagram | 900 | UHF Feceiver H4 Frequency for Wireless Announcements patched intot the sound system with one (1) up to 6 Channel Analog Mixer | Yes | BARS FROM AMPA EVENTS TO BE SET AND READY BETWEEN 10AM AND 4PM (KATLYN 804-516-4127; NO POSTER SESSIONS ON THE SHOW FLOOR THAT EVENING; AMPA EVENTS WILL UNLOAD BY 9:45PM AND THE POSTER SESSIONS WILL MOVE IN THIS ROOM AFTER THE EVENT BY EXHIBITS INC. | Please note, we do not want the poster sessions in the Exhibit Hall room fro this event. We will want them set after the reception
8AM-MIDNIGHT | Set up GS room | RCC-Ballroom | See Diagram | 1500 | Ballroom stage lighting; three (3) 10.5 x14' frame and legs; (rear projection); 10.5x14 Deluxe Dress Kit Black; Three (3) staged in each section of the ballroom -12K lumen DLP 1920-1080 Projector: 4:3 Ratio; Three (3) Short Fixed LCD Lens; and support package; Three 42 inch LCD teleprompters and mirror content on large screen; (3) three 4 output VGA DA (split signal from video to conference monitor and screen; Three (3) Video Switcher scaling 8x1; Six (6) Sigle UGF Receiver H4 Frenguency; six (6) Headset Microphone (countryman style): three (3) Passive Direct Box (with audio patch into sound system); Three (3) Channel Analog Mixer with volume control; three (3) small GAV Cable Lot | No | See Diagram; GS Stage set with headtable fro four people (one of which will be the student helping the session) We will need a timer in this room--Todd to ask Anthony for the best way to have this purpose served--I did tell Todd we have a teleprompter on the a/v equipment | ANTHONY, ANITA AND TRS
Monday, May 4, 2015-HOTEL SHUTTLE WILL RUN FROM 7:45AM-6:45PM; CHAIRMAN'S RECEPTION BY INVITATION ONLY FROM 6PM-9PM
Date/Time | Event | Location/Room Name | Room Set-up | # of people | AV |  | NOTES | POC
24 hour hold | Editorial Room | RCC-E11-B | two computer work stations per 6 ft table facing doors. Must be locked | 29 | existing | yes | Existing | Staff to be provided by Jefferson Lab
24 hour hold | Authors/Editors F&B and Storage | RCC-E11-C | rounds with tables for food | 35 | no A/V | yes
24 hour hold | Authors Reception Room | RCC-E11A | four six foot tables flush to the wall with printer and binders on the back walls. Three six foot tables facing the door with two computer work stations | 7 | existing | yes | Existing | Staff to be provided by Jefferson Lab
24 hour hold | Paper Café | RCC-E10C | Existing |  | existing | yes | yes, tbd | Staff to be provided by Jefferson Lab
24 hour hold | Speaker Ready Room | RCC-E10D | Existing |  | existing | yes | yes, tbd | Staff to be provided by Jefferson Lab
24 hour hold | Business Office | RCC-Registration 1 | Existing |  | existing | yes | yes, tbd | Staff to be provided by Jefferson Lab
24 hour hold | Staff Office Breakroom | RCC-Registration 2 | Existing | 25 | no A/V | yes
24 hour hold - Registration Open 8AM-6PM | Registration | RCC-Lobby |  |  | existing | yes | Existing | Anita to hire 8 people to work the registration desk
24 hour hold | Press Room | RCC-E22-A | (6) six foot tables set as workstations with internet connections and power supply hookups; room will have camera area in corner as well. | 6 | existing | yes |  | John will be in charge of this room for PR
24 hour hold | Storage | RCC-E10A |  |  | no A/V | No | yes, tbd
6am-NOON (session time from 9AM12:30PM) Note-9:15AM Secretary of Education will be present | Opening Session-9-10:30 Andrew; 9-930-Welcome of Chairs, Welcome from Virginia Secretary of Education, Anne Holton; 930-10 Commissioning and Operations of CEBAF at 12 GeV-Arne Freyberger; 10-10:30 LHC Commissioning at Higer Energy-Paul Collier (CERN) | RCC-Ballroom | see diagram | 1500 | existing | yes, stay and photograph the entire session please | See Diagram
8-10am | Marriott--Companion Breakfast | Marriott--Ballroom G-J | half rounds of 7 | 70 | LCD and support package --note, contracted to use the Marriott's A/V team for all meeting space at the Marriott | Yes, can Jeannie take some pictures of this event | half rounds | Anita to coordinate Richmond expert to discuss activities available and sign up; suggest opening food stations at the RCC on ala carte for breakfast and lunch
10:30am-11am | AM BREAK | Exhibit Hall A | Flow | 900 | existing | Yes of the exhibit hall |  | Coffee, Tea and Decaf Please note the convention center will have the café open at 7AMbreakfast
11:30AM-2PM | APS-DPB Business Meeting | RCC-E10B | RECEPTION with chairs around the perimeter of the room; will have a light reception of finger food, snacks and bar available for 2 hours from NOON-2PM | 40 |  | YES | May want a bar in the room | we plan and pay. confirmed with Fulvia via Stan Shriber; WILL BE POSTED TO THE MASTER ACCOUNT AGAINST THE APS LOAN
NOON-2PM | Lunch Break on own | Please note we will use this time to change the GS room to the breakout rooms |  |  |  | No |  | RCC to open lunch options in the café and on the show floor RCC CAFÉ to open from 11AM-3PM
2pm-4pm | Breakout/Paralleel Session | RCC-Ballroom A | theater | 700 | Ballroom stage lighting; one (1) 10.5 x 14 Frame & Legs screen centered behind stage-rear projection; 1 10.5 x 14 Deluxe dress kit; 12K lumen DLP 1920x1080 projector and support package; one (1) LCD Monitor for confidence moniter; 4 output VGA DA (splits signal from video source to send it to the conference moniter and large screens; 1 Video Switcher Scaling 8x1 for seamless switching; Single UHF Receiver H4 Frequency; two (2) Headset microphones; 1 passive direct box (PC audio into house sound) mixer; two (2) wireless microphones for question and answers | Yes | Stage Set will need podium with wireless microphone; headtable for 4 (one of which will be the student)
2pm-4pm | Breakout/Paralleel Session | RCC-Ballroom B | theater | 700 | Set previous day as the GS; need to have two wireless microphones for question and answer sessions | Yes | Stage Set will need podium with wireless microphone; headtable for 4 (one of which will be the student)
2pm-4pm (MAY NOT USE) | Breakout/Paralleel Session | RCC-Ballroom C | theater | Max Set | Ballroom stage lighting; one (1) 10.5 x 14 Frame & Legs screen centered behind stage-rear projection; 1 10.5 x 14 Deluxe dress kit; 12K lumen DLP 1920x1080 projector and support package; one (1) LCD Monitor for confidence moniter; 4 output VGA DA (splits signal from video source to send it to the conference moniter and large screens; 1 Video Switcher Scaling 8x1 for seamless switching; Single UHF Receiver H4 Frequency; two (2) Headset microphones; 1 passive direct box (PC audio into house sound) mixer; two (2) wireless microphones for question and answers | Yes | Stage Set will need podium with wireless microphone; headtable for 4 (one of which will be the student) | Anita's staff to be responsible for the room set; audio visual and signage---Fulvia to assign persons responsible for speaker content
24 hour hold EXHIBIT HALL OPEN 8AM-6PM; Poster sessions run from 4-6pm | Exhibit Hall and Poster Sessions with break | RCC-Exhibit Hall A |  | 800 | existing | Yes |  | Anita will have one person on the floor as contact; FOUR SECURITY OFFICERS WILL NEED TO BE HIRED FROM 7:30AM-6PM; TWO SECURITY OFFICERS FROM 6PM-7AM
4pm-6pm | Poster Sessions Open | RCC-Exhibit Hall A |  | 900 | existing | Yes
4:15-4:45PM | LOC Brief Staff Meeting | Business Center |  | 15 |  | Yes |  | Fulvia to lead
5:30pm-8:30pm | Meet the PRST-AB Editors | RCC-Registration Lobby Foyer | reception | 300 |  | Yes | Organized on Monday by and hosted by APS working with Jennifer from APS | APS--Jennifer is working with Teresa on this event
5:30PM-7PM | SLAC Meeting | Marriott Salons 1-4 | U-Shape | 40 |  | No |  | Zenghai Li
5PM-7PM | AAC2016 Organizing Committee | RCC-E-10B | U-Shape; 2 per 6 ft | 40 | will need lcd and support package with speaker phone in the room | No |  | Dr. Dan Gordon
6pm-8:30pm | Open XAL Workshop I-Future Directors, hosted by Oak Ridge National Laboratory Spallation Neutron Source | Marriott--Salons G-J | Classroom 2 per 6 ft. | 40 | LCD and support package --note, contracted to use the Marriott's A/V team for all meeting space at the Marriott | No |  | per Mr. Pelaia they are expecting only 15 people in attendance; Approved via Fulvia-billing still pending
6:30-8:30pm | Chairmans Reception-By Invitation Only | Jefferson Hotel |  | 275 | will need stage with audio visual for performers (pending discussion with the hired company) | Yes, please take lots of pictures |  | Tina and Stephanie to volunteer with Jeannie to collect tickets from 6:30-7:30pm
Tuesday, May 5, 2012- Hotel shuttle runs fro,m 7:45AM-6:45PM
Date/Time | Event | Location/Room Name | Room Set-up | # of people | AV |  | NOTES | POC
24 hour hold | Editorial Room | RCC-E11B | two computer work stations per 6 ft table facing doors. Must be locked | 29 | existing | Yes | Existing | Anthony
24 hour hold | Authors/Editors F&B and Storage | RCC-E11C | rounds with tables for food | 35 | no A/V | Yes |  | Anthony
24 hour hold | Authors Reception Room | RCC-E11A | four six foot tables flush to the wall with printer and binders on the back walls. Three six foot tables facing the door with two computer work stations | 7 | existing | Yes | Existing | Anthony
24 hour hold | Press Room | RCC-E22-A | (6) six foot tables set as workstations with internet connections and power supply hookups; room will have camera area in corner as well. | 6 | existing | Yes |  | John will be in charge of this room for PR
24 hour hold | Paper Café | RCC-E10C |  |  | existing | Yes | Existing | Anthony
24 hour hold | Speaker Ready Room | RCC-E10D |  |  | existing | Yes | Existing | Anthony
24 hour hold | Business Office | RCC-Registration 1 | Existing | 2 | existing | No | Existing | Anita
24 hour hold | Staff Office Breakroom | RCC-Registration 2 | Existing | 20 | no A/V | no | Existing
24 hour hold - Registration Open from 8AM-6PM | Registration | Registration Lobby |  |  | existing | Yes | REZA TO SEND OUT A BLAST EMAIL OR BANNER ADS FOR TOP SPONSORS | Anita to provide 2 staff members
24 hour hold | Storage | RCC-E10A |  |  | no A/V | No | Existing | Anita
6:30am-10am | Past TC ExCom Meeting with Breakfast from 6:30AM with coffee station | RCC-Governors Room(note need to flip room for afteroon event beginning at 11:30AM) | CONFERENCE seating VIP set; 2 per 6 ft | 13 | LCD projector and support package; Will need abilities for MAC and PC in the support package wiring they will both need to project onto the video projector and have sound; we will need power strips, secured in this room; VIP set; TRS please add | Yes | please note this room will need to be flipped for a meeting starting at 11AM | We plan and we pay. will need breakfast, coffee station and bottled water on the tables; need to know who to send menu options and what the payment process will be; THIS WILL BE BILLED TO THE CONFERENCE TOWARD THE IEEE NTSS
24 hour hold Exhibit Hall Open from 8:30AM-6pm | Exhibit Hall and Poster Sessions with AM Break from 10-10:30AM and 2-230 PM Beverage Break on the show floor) | RCC-Exhibit Hall A |  | 1000 | existing | Yes |  | Anita will have one person on the floor as contact; FOUR SECURITY OFFICERS WILL NEED TO BE HIRED FROM 7:30AM-6PM; TWO SECURITY OFFICERS FROM 6PM-7AM
9am-6pm (note Tuesday 9-12:30pm only 2 breakout rooms and 12:30-4pm 3 breakout sessions | Breakout/Paralleel Session | RCC-Ballroom A | theater | 700 | existing | Yes | see diagram
9am-6pm | Breakout/Paralleel Session | RCC-Ballroom B | theater | Max Set | existing | Yes | see diagram
9am-6pm (May not use) | Breakout/Paralleel Session | RCC-Ballroom C | theater | 700 | existing | Yes | see diagram
11AM-2PM (room flipped from breakfast | Past TC Business Meeting | RCC-Governors Room | RECEPTION with chairs around the perimeter of the room; will have a light reception of finger food, snacks and bar available for 2 hours from NOON-2PM | 40 | no audio visual requested | yes | Reception set | confirmed via Fulvia with Stan Shriber will need finger foods and bar from NOON-2pm; need to know who to send menu BILLED TO THE MASTER AGAINST THE IEEE LOAN
11:30AM-2:30PM | LINAC'16 IOC | Marriott-Salon 5 | U-Shape; 2 per 6 ft | 30 | LCD and support package --note, contracted to use the Marriott's A/V team for all meeting space at the Marriott | no |  | Amy McCausey contact
NOON-4PM | APS-PRST/AB Editorial Board Meeting | RCC-E10B | U-Shape; 2 per 6 ft | 30 | LCD and support package; TRS will need | Yes |  | Contact Jennifer Wildermuth APS WILL DO VIDEO CONFERENCE-ANTHONY AND JENNIFER WILL WORK ON THIS PRIOR TO THE MEETING
1pm-6pm | Spin Tracking for Precision Measurements Presented by: Brookhaven National Laboratory | Marriott- Salon A/B | U-Shape; 2 per 6ft | 40 |  | No |  | Approved via Fulvia-billing options stil pending Mei Bai has requested this meeting both May 5 and May 6th;
12:30pm-2pm | Lunch Break on own | on own |  |  |  | No |  | RCC please open café and on show floor for lunch options; Lunch open from 11-3pm
4pm-6pm | Poster Sessions and Exhibit Hall Open | RCC-Hall A |  | 900 |  | yes
4:15-4:45PM | LOC Brief Staff Meeting | Business Center |  | 15 |  | yes |  | Fulvia to lead
6pm-8pm | Marriott--IPAC15 OC Dinner | Governors Room | U-Shape; 2 per 6 ft | 40 | CONFIRMED NO A/V NEEDED BUT WE WILL HAVE A/V IN THAT ROOM PRE-SET AND WILL DO THE DINNER SET WORKING AROUND THE A/V | Yes |  | CONFIRMED THIS IS STAYING
Wednesday, May 6, 2012-Hotel Shuttle from 7:45AM-10:30PM
Date/Time | Event | Location/Room Name | Room Set-up | # of people | AV |  | NOTES | POC
7am-9am | Rehearsal time for Women in Science | Ballroom B | Existing | 700
24 hour hold | Editorial Room | RCC-E11B | two computer work stations per 6 ft table facing doors. Must be locked | 29 | existing | Yes |  | Staff and volunteers to be provided by Jefferson Lab
24 hour hold | Authors/Editors F&B and Storage | RCC-E11C | rounds with tables for food | 35 | no A/V | yes
24 hour hold | Authors Reception Room | RCC-E11A | four six foot tables flush to the wall with printer and binders on the back walls. Three six foot tables facing the door with two computer work stations | 7 | existing | yes |  | Staff and volunteers to be provided by Jefferson Lab
24 hour hold | Press Room | RCC-E22-A | (6) six foot tables set as workstations with internet connections and power supply hookups; room will have camera area in corner as well. | 6 | existing | yes |  | John will be in charge of this room for PR
24 hour hold | Paper Café | RCC-E10C |  |  | existing | yes |  | Staff and volunteers to be provided by Jefferson Lab
24 hour hold | Speaker Ready Room | RCC-E10D |  |  | existing | YES |  | Staff and volunteers to be provided by Jefferson Lab
24 hour hold | Business Office | RCC-Registration 1 |  |  | existing | no |  | Staff and volunteers to be provided by Jefferson Lab
24 hour hold | Staff Office Breakroom | RCC-Registration 2 |  | 15 | no A/V | yes
24 hour hold - Registration Times 8AM-6PM | Registration | Registration Foyer |  |  | existing | yes | Existing | Anita to provide 2 staff members; Jefferson Lab to provide 6 temp or volunteers
24 hour hold Exhibit Hall Open from 8:30AM-6PM; Exhibit Hall Dismantle from 6-9pm | Exhibit Hall and Poster Sessions | RCC-Exhibit Hall A |  | 900 | existing | yes |  | Anita will have one person on the floor as contact; FOUR SECURITY OFFICERS WILL NEED TO BE HIRED FROM 7:30AM-6PM; TWO SECURITY OFFICERS FROM 6PM-7AM
4:15-4:45PM | LOC Brief Staff Meeting | Business Center |  | 15 |  | yes |  | Fulvia to lead
6:30am-8:30am | IEEE Member Reception | Marriott--Salon 6-8 | Rounds of 6/8 with buffet breakfast station | 150 | no A/V | yes | Buffet Breakfast $25 inclusive pp. | will need breakfast, coffee station and bottled water on the tables; TO BE DIRECT BILLED AND WILL BE CHARGED AGAINST THE IEEE LOAN
24 hour hold | Storage | RCC-E10A |  |  | no A/V | no
9am-5pm (Note: 9-12:30AM two breakout rooms to be used and 2-4pm three breakout rooms to be used. | Breakout/Paralleel Session | RCC-Ballroom A | theater | 700 | existing | yes
9am-5pm | Session for Industry in Ballroom B only | RCC-Ballroom B | theater | Max Set | existing | Yes | Needs a headtable for 12 people (one microphone on table stands) for every two persons
9am-5pm | Breakout/Paralleel Session | RCC-Ballroom C | theater | 400 | existing | yes
10:30am-11am | AM Break | RCC-Exhibit Hall A |  | 700 |  |  |  | coffee, tea, decaf
8AM-6PM | Poster Sessions and Exhibit Hall Open | RCC-Hall A |  | 900 | existing | yes
12:30-2PM | IPACCC | Marriott-Apple Board Room | Conference Style | 12 | no audio visual requested | Yes | Board room with max seating for 12 people around the table | Andrew Hutton is the lead; Anita to arrange lunch; this is on the master account
1pm-6pm (have reminded Mei Bai there will be a meeting in the room at 6:15pm and will need to vacate at or before 6pm | Spin Tracking for Precision Measurements Presented by: Brookhaven National Laboratory Part II | Marriott Salon A/B | Classroom 2 per 6 ft. | 40 |  | No |  | Contact Mei Bai
6pm-8pm; reception from 8-10pm | Women In Science & Engineering with reception in foyer from 8-10pm Moderator Patrizia Rossi; Panelist-Elke Aschenauer, Barbara Boyan, Latifah Elouadrhiri, Haiyan Gao, Fabiola Gianotti, Thia Keppel, Young-Kee Kim, Liu Lin, Alena Opper, Fulvia Pilat; | RCC-BALLROOM B | theater; need headtable on LARGE stage to accommodate 12 panelists. We willl need to add wireless microphones for each presenter on stands | Existing set | Web conferencing with Adobe Connect or the like, one Apple Mac Book Pro 13 inch Z0MU to facilitate conference wth video, audio and content from presenters remotely; 1 Digital Audio Interference Box for dedicated Audio from host site, stage with LCD and support package with front screen projection; we will need to do a rehersal for this event-time TBA: need to add 12 microphone on stands for the panelists---CHAD | Yes, please take picturs of the entire event. Meeting to the reception | theater set see diagrams for options. Need to call in 3/4 people in the meeting; will need to schedule a rehearsal time for this event with A/V and LOC. Need the room set and ready by 4pm; see diagram for set up options; Needs a headtable for 12 people (one microphone on table stands) for every two persons | 50 particiants from the local area with keynote speakers of Fabioa Gianotti-CERN Director General (remotely) Hayan Gao Vice Chancellor for academica affairs at Kuke Kunshan University in China (remote). We will be video conferencing the attendees via skype
6:15-8pm | Open XAL Workshop I | Marriott Salon A/B | Classroom 2 per 6 ft. | 40 | LCD and support package --note, contracted to use the Marriott's A/V team for all meeting space at the Marriott | No | Classroom | per Mr. Pelaia they are expecting only 15 people in attendance; Approved via Fulvia-billing instructions still needed
Thursday, May 7, 2015-Hotel Shuttle from 7:45AM-11:45PM
Date/Time | Event | Location/Room Name | Room Set-up | # of people | AV |  | NOTES | POC
24 hour hold | Editorial Room | RCC-E11B | two computer work stations per 6 ft table facing doors. Must be locked | 29 | existing | Yes
24 hour hold | Authors/Editors F&B and Storage | RCC-E11C | rounds with tables for food | 35 | no A/V | yes
24 hour hold | Authors Reception Room | RCC-E11A | four six foot tables flush to the wall with printer and binders on the back walls. Three six foot tables facing the door with two computer work stations | 7 | existing | yes
24 hour hold | Press Room | RCC-E22-A | (6) six foot tables set as workstations with internet connections and power supply hookups; room will have camera area in corner as well. | 6 | existing | yes |  | John will be in charge of this room for PR
24 hour hold | Paper Café | RCC-E10C |  |  | existing | Yes
24 hour hold | Speaker Ready Room | RCC-E10D |  |  | existing | Yes
24 hour hold | Business Office | RCC-Registration 1 |  |  | existing | No
24 hour hold | Staff Office Breakroom | RCC-Registration 2 |  |  | existing | No
24 hour hold - Registration from 8AM-NOON | Registration | RCC-Registration Foyer | Soft close at NOON to allow for the poster session; Dismantle after 4pm |  | existing | Yes | Existing | Anita to provide 2 staff members; Jefferson Lab to provide 6 temp or volunteers
6:30am-10am | PAC-OC Meeting with Breakfast | RCC-E10B | U-Shape; 2 per 6 ft with chairs flush to the wall around the perimeter of the room; | 22 | LCD projector and support package; Will need abilities for MAC and PC in the support package wiring they will both need to project onto the video projector and have sound; we will need power strips, secured in this room; VIP set; we will need a telecomm in the room for people to call in to the meeting | Yes |  | will need breakfast, coffee station and bottled water on the tables; need to know who to WILL BE ON THE MASTER ACCOUNT
8AM-NOON | Set up Marriott F-J for the Awards Ceremony | Marriott F-J | theater with large stage and thre screens. |  | approved that TRS will be able to set up | Not for set up but will be in the room for the entire Awards Ceremony
24 hour hold | Storage | RCC-E10A |  |  | no A/V | no |  | Anita
Dismantle DAY | Exhibit Hall and Poster Sessions (move poster sessions in the foyer area at registration) | RCC-Exhibit Hall A |  |  | no A/V | no |  | Anita
8am-9am | Continental Breakfast on OWN | RCC-Please open Café and concession stands |  | flow |  | no
8am-5pm | IPAC APS Teacher Day with Continental Breakfast and Lunch | MARRIOTT-SALON E | Salon E set in six (6) large rounds draped with ample space for floor activities between the tables; two head tables in the front of the room for paperwork; chairs around the perimeter of the room | 35 | this will be a group activity will need two wireless lavalier microphones and internet for the presenter; LCD projector with support package; Marriott to provide all audio visual | Yes |  | Brita
9am-NOON(Note: we will use all three sections all daywiththe add on of the V4 Meeting) | Breakout/Paralleel Session | RCC-Ballroom A | theater | 700 | existing | Yes
9am-NOON | Breakout/Paralleel Session | RCC-Ballroom B | theater | Max Set | existing | Yes
9am-NOON (MAY NOT USE) | Breakout/Paralleel Session | RCC-Ballroom C | theater | 700 | existing | Yes
10:30-11am | AM Break | RCC-Ballroom Foyer |  | 800 | no A/V | Yes
NOON-6PM (set up at 6AM) | Poster Sessions | Registration Foyer |  | 900 | no A/V | Yes | Existing
NOON-6pm | SET UP GALA | RCC-Ballroom---NO ACCESS TO THE ROOMS AFTER 12:30PM |  | 950 | existing
1:20PM-4PM (note there is a meeting scheduled at 4:15 and will need be cleared at 4pm) | TNS Special Edition | Marriott-Salons 1-4 | U-Shape; 2 per 6 ft | 40 |  | Yes |  | Yong Ho Chin
12:30-2:30PM | JACoW Stakeholders Meeting | RCC-E10B | classroom 2 per 6 ft with headtable in the front of the room for 3 persons | 80 | LCD projector and support package | Yes |  | Anita to provide light refreshments on the master account; per Christine what was listed as JACOW Steering Committee should be called JACOW Stakeholders Meeting
12:30pm-1:30pm | Lunch Break on own | on own
1:30pm-4:40pm | Awards Session runs from 2-3:20 and the 50th Anniversary of Accelerator Conferences from 3:20pm-4:40PM; Student poster prizes; IEEE/NPSS PAST Student Thesis Award Winner; APS/DPB Outstanding Doctoral Thesis Award; APS Wilson Prize Award--Special Session-Introductory REmarks; Accelerator Conferences in the US; Accelerator Conferencs in Asia; Accelerator Conferences in Europe, Conferences and World Peace | Marriott Salons F-J | theater with large stage and thre screens. | 660 | TRS to setup at 8am and tear down at 4:40pm | Yes, for the entire event please, after this event put the power point together for the presentation at the GALA | Riser with headtable to accommodate six (6) people-four awarded grantors, session chair and student helping the session; podium on the riser; need stairs on both sides of the stage
4:15PM-6:30PM | An Informational Session for Circular electron-positron Collider and Super proton-proton Collider (CepC-SppC) at Institute of High Energy Physics in China | Marriott-Salons 1-4 | U-Shape; 2 per 6 ft | 40 | Existing from previous meeting | No |  | IHEP; Yuhoung Zhang
5-6PM | IPAC'15 Debrief | RCC-E10B | classroom 2 per 6 ft with headtable in the front of the room for 3 persons | 80 | Existing from previous meeting | Yes |  | Andrew, Fulvia, Anita, Erin, Todd, Pam, Stephanie Anthony, Evelyn to present
7-11pm (change in time per Andrew so people will have time to change after the poster sessions) | GALA/Banquet | RCC-Ballroom A/B/C | Rounds | 950 | existing; pending if any additional will be needed | Yes | DJ on stage | Tina and Stephanie to volunteer with Jeannie to collect tickets from 7-8pm
Friday, May 8, 2015-Hotel Shuttle from 7:45AM-3:30PM; Airport Shuttle from 3PM-6PM
Date/Time | Event | Location/Room Name | Room Set-up | # of people | AV |  | NOTES | POC
teardown by midnight | Editorial Room | RCC-E11C | two computer work stations per 6 ft table facing doors. Must be locked | 29 | existing | No | Existing
teardown by midnight | Authors/Editors F&B and Storage | RCC-E11B | rounds with tables for food | 35 | no A/V | No | Existing
teardown by midnight | Authors Reception Room | RCC-E11A | four six foot tables flush to the wall with printer and binders on the back walls. Three six foot tables facing the door with two computer work stations | 7 | existing | No | Existing
teardown by 5pm | Paper Café | RCC-E10C |  |  | existing | No | yes, tbd
teardown by 5pm | Press Room | RCC-E22-A | (6) six foot tables set as workstations with internet connections and power supply hookups; room will have camera area in corner as well. | 6 | existing | No |  | John will be in charge of this room for PR
teardown by 5pm | Speaker Ready Room | RCC-E10D |  |  | existing | No | existing
teardown by 5pm | Business Office | RCC-Registration 1 |  |  | existing | No | yes, tbd
teardown by 5pm | Staff Office Breakroom | RCC-Registration 2 |  |  | existing | No | yes, tbd
teardown by 5pm | LUGGAGE STORAGE | RCC-E10A |  |  |  | No |  | Anita to hire staff to collect luggage
8am-9am | Continental Breakfast on OWN please open café | RCC |  | 700 | no A/V | No
9am-10:30am | Breakout/Paralleel Session | RCC-Ballroom AB | theater | MAX | existing | No
9am-10:30am | Breakout/Paralleel Session | RCC-Ballroom C | theater | 700 | existing | No
10:30-11am | AM Break | Ballroom foyer |  | 300 |  | No |  | Coffee, tea and decaf
11-12:30pm | Closing Remarks | RCC-Ballroom B | theater | 800 | existing | Yes
Noon-7pm | IPAC'16 SPC Meeting | RCC-E23A/B | Classroom 2 per 6 ft. | 40 | Need from Christine | No |  | Christine Petit-Jean-Genaz; approved via Fulvia; sent Christine menus and requested audio visual
teardown by 8pm | all meeting rooms | RCC
Saturday, May 9, 2015
Date/Time | Event | Location/Room Name | Room Set-up | # of people | AV |  | NOTES | POC
teardown by 5pm | Storage | RCC-E10A |  |  | no A/V
8am-7pm | IPAC'16 SPC Meeting | RCC-E23A/B | Classroom 2 per 6 ft. | 40 | existing | No |  | Christine Petit-Jean-Genaz